## Sheet
area | task | impact | effort | owner | window | notes
Digital | Fix keyboard traps on agenda archive filter | High | Medium | IT + vendor | 0-30 days | Replace div-based buttons w/ semantic controls and focus outline
Digital | Update agenda portal color palette for contrast | Medium | Low | Web vendor | 0-30 days | Adopt #0f172a text on light backgrounds per WCAG 1.4.3
Documents | Remediate next 10 council packets | High | High | Clerk + Civic ADA Desk | 0-30 days | Provide agendas 48 hrs prior to posting for tagging
Documents | Convert top 5 public forms to accessible PDFs | High | Medium | Clerk staff | 30-90 days | Start with permit + rec forms
Facilities | Replace handwritten service counter signage | Medium | Low | DPW | 0-30 days | Use tactile/Braille placards and queue signage
Facilities | Audit parking pay stations for reach + instructions | Medium | Medium | DPW | 30-90 days | Add large print + QR for audio instructions
Communications | Publish ADA contact + accommodation process on homepage | High | Low | Clerk | 0-30 days | Match DOJ template and link from footer
Training | Host 1-hour ADA communications refresher | Medium | Low | HR | 30-90 days | Include agenda formatting SOP